## Sheet1
| Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Midsem Break | Week 10 | Week 11 | Week 12 | Week 13
Design Planning
Web App Design | bar: Week 4; Week 6
Web App File Processing | bar: Week 4 to Week 5
Web App Music Writer | bar: Week 6 to Week 8
DLL Communication | bar: Week 4 to Week 6
Simple Audio Playback | bar: Week 4
Baton Sensing | bar: Week 4 to Week 6
Tempo Control | bar: Week 6 to Week 7
System Integration | bar: Week 8 to Week 9
Bug Fixes
Bonus Features